## Sheet1
Group Name | Team Members | March |  |  |  | April |  |  |  | May |  |  |  | June
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | Notes
WP Leading Group: Manager: Yuxiang Yao | Yao Yuxiang,Yang yang
Task 1.1: Hold the meating to organize the meeting | Yao Yuxiang,Yang yang
Task 1.2: Determine the time plan for this project | Yao Yuxiang,Yang yang
Task 1.3: Gather the information for weekly update from each member | Yao Yuxiang,Yang yang
Task 1.4: Determine the overall design, make the decision of the user-logic | Yao Yuxiang,Yang yang
WP Deployment Group: Manager: Hu Siyang | Hu Siyang, Yao Yuxiang
Task 2.1: Rent a server and domain name | Hu Siyang, Yao Yuxiang
Task 2.2: Setting up a server environment | Hu Siyang, Yao Yuxiang
Task 2.3: Send the file to the server and integrate code | Hu Siyang, Yao Yuxiang
Task 2.4: Test the project on the established server | Hu Siyang, Yao Yuxiang
WP Front-End-Code Group: Manager: Li Zigen | Li Zigen, Yao Yuxiang
Task 3.1: Determine how many pages that the website needs and distinguish the different functions that the page takes responsibility for | Li Zigen, Yao Yuxiang
Task 3.2: Design pages for website and find resources that will be used | Li Zigen, Yao Yuxiang
Task 3.3: Connect back-end functions with front-end and fix problems | Li Zigen, Yao Yuxiang
Taks 3.4: Adding some wonderful effects on the website and checking all pages | Li Zigen, Yao Yuxiang
WP Back-End-Code Group: Manager: Yuan Qitong | Yuan Qitong, Li Zigen
Task 4.1: Searching information and good examples | Yuan Qitong, Li Zigen
Task 4.2: Give discussion with Customer Group and Front-End-Group | Yuan Qitong, Li Zigen
Task 4.3: Coding | Yuan Qitong, Li Zigen
Task 4.4: Debugging and try to find if any requiremnt has not achieved | Yuan Qitong, Li Zigen
Task 4.5: Giving help in final deployment | Yuan Qitong, Li Zigen
WP 1: Customer Manager: Yang Yang | Yang Yang, Yuan Qitong
Task 1: Communicate with customers | Yang Yang, Yuan Qitong
Task 2: Follow up with customers | Yang Yang, Yuan Qitong
Task 3: Track the user experience. | Yang Yang, Yuan Qitong
WP 1: Maintenance Manager: Xi Huakai | Xi Huakai Husiyang
Task 1.1: 1. Maintained the server and related hardware and software, evaluated the possible problems and established the response time; | Xi Huakai Husiyang
Task 1.2:Update and adjust contents | Xi Huakai Husiyang
Task 1.3: Formulated regulations on website maintenance, institutionalized and standardized website maintenance; | Xi Huakai Husiyang
Task 1.4: do a good job of website security management, , check the website functions, links are wrong. | Xi Huakai Husiyang